## Summary
Field | Value
Report purpose | Instructor-facing experiment log for the hallucination mitigation project. It lists completed, failed, interrupted, active, and queued experiments discussed/executed in this chat.
Generated | 2026-04-26 15:01
Main caution | No API keys are included. Proprietary APIs are named only by provider/model.
Current main training | HSA-DPO, LLaVA-1.5-7B, released HSA-DPO preferences, effective batch 32, 1 epoch, active at last check.
Current baseline queue | Normal DPO, same LLaVA-1.5-7B/data/settings, queued to run after HSA-DPO finishes.
Best completed judgement result so far | OpenAI GPT-4o mini judgement over released preferences: 8386 rows, 2914 accepted, 5472 rejected.
Qwen detector outcome | Qwen2.5-VL-7B local detector training/inference path was attempted, but inference predicted 0 hallucinated rows; Stage 4 produced 0 preference pairs.

## Experiments
ID | Stage | Experiment | Models/Backends | Data/Input | Main settings | Status | Result/Observed output | Failure/Issue | Reason/Lesson | Artifacts
E01 | Stage 1 | Released fine-grained annotation parser | No model call; parses released HSA-DPO detection annotations | fg_pipeline/data/hsa_dpo_detection.jsonl | Parser-only; preserve critiques/severity labels | Completed | 16143 rows: 7643 hallucinated, 8500 non-hallucinated; about 7749 parsed critique items noted earlier | None; this is released supervision, not regenerated GPT/Gemini annotation | Paper-faithful enough for our budget because released annotations already represent D_faif. | output/fghd/stage1/* and later output/fghd/paper_stage1/d_faif.jsonl
E02 | Stage 2 | Original rewrite generation from critiques | LLaVA/template path depending on run; template only for smoke tests | Stage 1 hallucinated rows/critiques | Rewrite hallucinated responses using critique text | Completed earlier | Stage 2 outputs existed and were used by legacy Stage 3 validation | Prompt was shorter than paper appendix rewrite prompt | Useful for smoke/current pipeline, but less paper-faithful than detect-then-rewrite with detector outputs. | output/fghd/stage2/*
E03 | Paper Stage 1 | Paper-faithful D_FAIF build from released annotations | No model call; released annotation parser plus appendix prompt templates for reproducibility | fg_pipeline/data/hsa_dpo_detection.jsonl | Appendix-aligned metadata; preserve raw annotation text/source | Completed | 16143 D_FAIF records written; 7643 hallucinated and 8500 non-hallucinated | No failure | This is the clean paper-path source for detector/data experiments. | output/fghd/paper_stage1/d_faif.jsonl; output/fghd/paper_stage1/stats.json
E04 | Paper Stage 2 | Detector training dataset construction | No model call; dataset conversion | output/fghd/paper_stage1/d_faif.jsonl | Hallucinated target: typed critique/severity report; clean target: NO HALLUCINATION; deterministic ordering/sampling | Completed | 16143 detector examples written: 7643 hallucinated, 8500 non-hallucinated | Dataset had fewer non-hallucinated rows than ideal 1:1.2 ratio target (9172); used all 8500 | No validation split was used by user choice; use all data for detector dataset. | output/fghd/paper_stage2/detector_train.json; detector_split_stats.json
E05 | Legacy Stage 3 | Qwen/LLaVA ensemble validation speedup | Qwen-VL-Chat + LLaVA family ensemble | Stage 2 rewrites over 7643 rows | Initially 3 votes Qwen->LLaVA->Qwen; later early stop, resume, incremental writes, max tokens adjusted | Partially implemented / superseded | Speed/robustness code added; not kept as final research path | Missing qwen-side packages caused warnings/import failures: tiktoken, matplotlib, transformers_stream_generator; Qwen checkpoint loading was slow and repeated; generation config needed fixing | Heavy local model voting was too slow and brittle for the one-box workflow; preflight checks and resume were necessary. | scripts/run_stage3_validate.sh; output/fghd/stage3/* legacy outputs
E06 | Legacy Stage 3 | Gemini + GPT-4o mini strict validation over rewritten Stage 2 output | Gemini 2.5 Flash-Lite + GPT-4o mini | 7643 rewritten rows from current Stage 2/Stage 4-era pipeline | Two-vote judgement; pass only under strict rule used at that time | Completed but not enough data | One run wrote 98 preference pairs and 7643 audit rows; an earlier logic issue showed 0 preference pairs when pass logic/path did not match Stage 4 input | Too strict for training: only about 98 accepted pairs, far below thousands needed | API validation can audit quality, but using it as the only gate can destroy dataset size. | output/fghd/stage3/vote_records.jsonl; output/fghd/stage3/preference_pairs.jsonl; stats.json
E07 | Legacy Stage 4 | Repair rows rejected by API validation | LLaVA-1.5-13B initially, later LLaVA-1.5-7B after storage/time tradeoff | Rejected/failed rows from Stage 3 validation | LLaVA repair/rewrite, resumable; deterministic local generation | Completed in one run | Stage 4 repair wrote 7545 repair pairs and 7643 final preference pairs in the current/legacy path | Long runtime; LLaVA checkpoint loading and generation were slow; model-size/storage constraints pushed move from 13B to 7B | Repair can restore dataset volume after strict validation, but it is costly and not exactly paper detector->rewrite methodology. | output/fghd/stage4/repair_records.jsonl; output/fghd/stage4/final_preference_pairs.jsonl; stats.json
E08 | Legacy Stage 5 | Severity-margin HSA-DPO on legacy Stage 4 pairs | LLaVA-1.5-13B initially, LoRA, DeepSpeed ZeRO-3 | output/fghd/stage4/final_preference_pairs.jsonl | 2 epochs; LoRA r=128 alpha=256; LR=2e-6; total batch 32; beta=0.1; freeze projector; severity_margin loss | Completed earlier | Training completed at global_step=476; evaluation preflight confirmed trainer_state global_step=476 | Initial OOM on 48GB for 13B/large settings; ZeRO-3 no_sync incompatibility needed trainer patch; runtime long | Trainer compatibility patches were required; 13B is expensive for single 48GB GPU. | output/fghd/stage5_llava_margin/checkpoint-476; trainer_state.json
E09 | Evaluation | Automatic evaluation runner without external judge APIs | LLaVA-1.5 base vs Stage 5 LoRA; automatic metrics only | POPE adversarial, Object HalBench, AMBER assets | No OpenAI/Gemini judge; run names stage5_auto_eval_smoke/full; temperature=0, max_new_tokens=512 | Set up / partial run | Preflight initially failed because benchmark assets were missing; assets then installed; full run was started and later stopped so user could control run | Missing benchmark files/images at first; transient Hugging Face DNS warning for CLIP config; evaluation outputs already existed unless CLEAN_EVAL=1 | Evaluation must separate automatic metrics from judge-based benchmarks for fair comparison. | scripts/run_stage5_eval_auto.sh; scripts/setup_stage5_eval_assets.sh; output/eval/stage5_auto_eval_*
E10 | Vast/storage | Move from 1x 48GB instance to 2x/other instances and cleanup | Infrastructure only | Volume Local-35489770 and later no-volume instance attempt | Clean unneeded models/checkpoints; remove models/Qwen-VL-Chat; archive outputs; transfer attempt cancelled | Completed cleanup / cancelled transfer | Qwen-VL-Chat removed; old checkpoint/output cleanup performed; later no-volume transfer attempt cancelled and temp transfer files removed | No-volume instance required copying 20GB+ assets; user cancelled instance and transfer | Use same Vast volume for fast instance switching; otherwise copy only minimal assets. | No final research artifact; infrastructure state only
E11 | Paper Stage 3 | LLaVA detector training attempt | LLaVA-1.5-13B detector LoRA path | output/fghd/paper_stage2/detector_train.json | 2 epochs; LoRA r=128 alpha=256; LR=1e-5; batch target 16; model_max_length initially 2048/other variants | Failed / abandoned | Training failed at first due to import path issue: No module named llava | Repo path/module import mismatch for LLaVA training script in this environment | LLaVA detector path required deeper environment fixes; we switched to Qwen2.5-VL detector attempt for implementation stability, then later abandoned local detector path. | scripts/run_paper_stage3_detector_train.sh; output/fghd/paper_stage3/detector_lora partial/none
E12 | Paper Stage 3 | Qwen2.5-VL-7B detector setup/download | Qwen2.5-VL-7B-Instruct | output/fghd/paper_stage2/detector_train.json | LoRA detector training; output temporary /tmp/qwen_detector_lora_tmp; MODEL_MAX_LENGTH eventually 1024 | Setup completed; training attempt proceeded | Model downloaded to models/Qwen2.5-VL-7B-Instruct; initial no-space issue solved by removing old assets and using /tmp output | No space left during model download; needed cleanup and external/tmp output location | Large model storage must be planned separately from project volume outputs. | models/Qwen2.5-VL-7B-Instruct; /tmp/qwen_detector_lora_tmp during run
E13 | Paper Stage 3 | Qwen2.5-VL detector training first errors | Qwen2.5-VL-7B-Instruct + LoRA | paper_stage2 detector_train.json | Initially used Trainer args including evaluation_strategy; later max length 512 then 1024 | Failed then fixed | First error: TrainingArguments got unexpected keyword argument evaluation_strategy. Second error: image features and image tokens do not match (tokens 497, features 999). Rerun with MODEL_MAX_LENGTH=1024 proceeded. | Transformers version mismatch and image-token truncation mismatch at too-short max length | Version-compatible argument handling and enough sequence length are required for Qwen2.5-VL image tokens. | fg_pipeline/paper/run_stage3_qwen_train.py; scripts/run_paper_stage3_qwen_train.sh before removal
E14 | Paper Stage 3 | Qwen2.5-VL detector inference after training | Qwen2.5-VL-7B detector LoRA | 16143 paper_stage2 rows | BACKEND=qwen_detector; MODEL_BASE=models/Qwen2.5-VL-7B-Instruct; MODEL_PATH=paper_stage3/qwen_detector_lora | Failed as detector | Stage 3 detect wrote 16143 detection rows but 0 predicted hallucinated; Stage 4 then wrote 0 preference pairs and 0 rewrite records | Detector collapsed to non-hallucination or parser/target-format did not recover hallucination outputs; not necessarily because Qwen is too small, more likely prompt/label/parser/calibration mismatch plus no validation split | A detector must be evaluated before using it to filter Stage 4. 0 positives means the downstream preference pipeline fails completely. | output/fghd/paper_stage3/detections.jsonl; detection_stats.json; output/fghd/paper_stage4/preference_pairs.jsonl empty
E15 | Paper Stage 4 | Direct paper-style rewrite using released annotations as detector substitute | LLaVA-1.5-7B rewriter | Released D_FAIF/paper-stage labels instead of failed learned detector | Use released annotations as H_i so all hallucinated rows can be rewritten; no API gate | Run started/used as fallback concept | Observed progress example: Paper Stage 4 rewrite around 855 rows at 6.46 it/s in one run; exact final result not recorded in chat before plan changed | This is not a learned detector reproduction; it uses released annotations directly | Fastest way to produce thousands of pairs when detector training fails, but should be reported as annotation-driven preference construction. | scripts/run_paper_stage4_rewrite.sh; output/fghd/paper_stage4/* when run
E16 | API Stage 3 | Released preference judgement with Gemini only | Gemini 2.5 Flash-Lite | hsa_dpo/data/hsa_dpo_preference_llava1dot5.jsonl, 8386 rows | API_JUDGE=gemini; decision_rule=either in script context; image-root hsa_dpo/data/images | Active at last check | Process still running; final output files not yet written at last check | No final counts available yet; script appears to write outputs at end | Gemini judgement is useful as a separate audit/filter pipeline, but should be separated from paper-faithful direct training. | output/fghd/released_pref_stage3/* target path
E17 | API Stage 3 | Released preference judgement with OpenAI only | GPT-4o mini | hsa_dpo/data/hsa_dpo_preference_llava1dot5.jsonl, 8386 rows | API_JUDGE=openai; openai_model=gpt-4o-mini; no API key stored in report | Completed | 8386 rows validated: 2914 accepted, 5472 rejected; stats written | Cost/time external dependency; results are model-judge dependent and not paper-faithful detector training | Good audit/filtering baseline, but should be reported separately from direct HSA-DPO training. | output/fghd/released_pref_stage3_openai/validated_preferences.jsonl; rejected_for_repair.jsonl; judgement_records.jsonl; stats.json
E18 | Qwen API idea | Qwen3-VL-Flash API judge idea | Qwen3-VL-Flash API (planned) | Released preferences / rewritten outputs | Would have used Qwen API key as an additional judge/filter | Cancelled before use | User decided to remove Qwen API/model usage and stick with current plan | Not executed; would add another external dependency and complicate the two-pipeline comparison | Keep final study simpler: direct training baseline plus optional Gemini/OpenAI judgement pipeline. | Qwen API code/env removed from active path
E19 | Stage 5 current | Direct paper HSA-DPO from released preference data, first batch16 attempt | LLaVA-1.5-7B + LoRA + DeepSpeed ZeRO-3 | hsa_dpo/data/hsa_dpo_preference_llava1dot5.jsonl; images hsa_dpo/data/images | EPOCH=2; TOTAL_BATCH_SIZE=16; DPO_LOSS_TYPE=hsa_weighted; USE_REJECTED_SCORE=True | Interrupted by user choice | Reached about 79/1048 steps earlier, then was cancelled to rerun faster settings | Long runtime for available time; not a code failure | Batch16 2 epochs is more thorough, but too slow for current deadline. | output/fghd/interrupted_stage5/stage5_paper_hsa_batch16_*.log; exp_direct_paper_hsa_* archive
E20 | Stage 5 current | Direct paper HSA-DPO, batch32 epoch1 | LLaVA-1.5-7B + LoRA + DeepSpeed ZeRO-3 | hsa_dpo/data/hsa_dpo_preference_llava1dot5.jsonl; images hsa_dpo/data/images | EPOCH=1; TOTAL_BATCH_SIZE=32; BATCH_SIZE=1; gradient_accumulation_steps=32; LoRA r=128 alpha=256; LR=2e-6; beta=0.1; DPO_LOSS_TYPE=hsa_weighted; USE_REJECTED_SCORE=True | Active at last check | Latest observed progress: 33/262 steps (13%); latest logged loss at step 30: 22.025; rewards/accuracy 0.5906; ETA about 4h13m at that snapshot | Warning: token sequence length 1083 > model_max_length 1024 for at least one row; training continued. This may truncate/affect a small number of long samples. | This is the current main paper-style HSA-DPO run, faster than batch16 2 epochs but fewer optimizer updates. | output/fghd/exp_direct_paper_hsa_b32_e1; output/fghd/stage5_paper_hsa_b32_e1.log
E21 | Stage 5 baseline | Normal DPO baseline, batch32 epoch1 | LLaVA-1.5-7B + LoRA + DeepSpeed ZeRO-3 | Same released preference data/images as HSA-DPO | EPOCH=1; TOTAL_BATCH_SIZE=32; DPO_LOSS_TYPE=standard; USE_REJECTED_SCORE=False; USE_CHOSEN_SCORE=False | Queued | Queue active and waiting for HSA-DPO batch32 epoch1 to finish | Not started yet due single GPU memory; cannot run concurrently with HSA-DPO | This provides the fair baseline against HSA-DPO using the same model, data, epoch count, and effective batch size. | scripts/run_direct_stage5_normal_dpo_batch32_epoch1.sh; output/fghd/exp_direct_normal_dpo_b32_e1 when complete
E22 | Stage 5 alternative | Our severity-margin HSA-DPO on released preference data | LLaVA-1.5-7B + severity_margin loss | Released HSA-DPO preference data | DPO_LOSS_TYPE=severity_margin; SEVERITY_MARGIN_SCALE=0.5; normalizer=3.0 | Planned then not run | Script existed but was not queued after user narrowed plan to paper HSA-DPO plus normal DPO | Excluded to keep comparison simple and fit time constraints | Useful future ablation, but not part of the current two-experiment setup. | scripts/run_direct_stage5_margin_hsa_batch16.sh earlier; not active
E23 | Methodology note | VLM fine-grained feedback and paper prompt alignment | Referenced paper: GPT-4V/GPT-4 for FAIF annotation, open-source LVLM detector, LLaVA rewrite; current final runs: LLaVA-1.5-7B | fg_pipeline/data/hsa_dpo_detection.jsonl and hsa_dpo/data/hsa_dpo_preference_llava1dot5.jsonl | Use released FAIF supervision; keep appendix-aligned prompts in fg_pipeline/paper/prompts.py; separate API audit/filter results from final DPO comparison | Documented | Added methodology note explaining VLM usage, prompt alignment, model rationale, and current two-experiment DPO comparison | Avoid claiming regenerated GPT-4/GPT-4V annotations; released annotations are used as supervision | This makes the instructor report clearer and separates paper-faithful supervision from diagnostic API/model experiments. | reports/vlm_fine_grained_feedback_methodology.md

## Models Used
Model | Role | Status | Notes
Qwen-VL-Chat | Local LVLM judge in legacy Stage 3 | Removed/superseded | Had missing packages and slow/repeated checkpoint loading; not used in final plan.
Qwen2.5-VL-7B-Instruct | Local detector candidate | Failed as detector | Training/inference path produced 0 predicted hallucinated rows; likely target/parser/calibration issue, not proven model-size issue.
Qwen3-VL-Flash | API judge idea | Cancelled | Setup idea removed to keep two-pipeline plan simple; no result.
Gemini 2.5 Flash-Lite | API judgement/audit/filter | Active run | No final counts at last check; no API key recorded.
GPT-4o mini | API judgement/audit/filter | Completed | 8386 judged; 2914 accepted, 5472 rejected; no API key recorded.
LLaVA-1.5-13B | Earlier rewrite/training candidate | Superseded | High VRAM/storage/time; OOM/slow single-GPU path.
LLaVA-1.5-7B | Current Stage 5 policy model and baseline | Active | Used for direct HSA-DPO and normal DPO; fits 48GB GPU with LoRA/ZeRO-3.
OpenAI CLIP ViT-L/14-336 | Vision tower for LLaVA | Dependency | Transient HF/DNS warning during evaluation; used by LLaVA pipeline.

## Lessons
Point | Note
Dataset size matters | Strict API filtering reduced one run to only 98 pairs, too small for strong DPO training.
Detector must be validated before Stage 4 | Qwen detector produced 0 positives, causing Stage 4 to emit 0 pairs.
Separate paper-faithful and API-audit pipelines | Released preferences/direct HSA-DPO is the clean baseline; Gemini/OpenAI judgement should be reported as a separate filtering/audit path.
Single 48GB GPU limits concurrency | HSA-DPO uses about 38.7GB VRAM; normal DPO must queue, not run concurrently.
Report exact protocol | Use same model/data/batch/epoch between HSA-DPO and normal DPO for fair comparison.
Avoid secret leakage | API keys were used/configured during work but are intentionally omitted from this report.

## Methodology Notes
Topic | Note
Purpose | Explain VLM fine-grained feedback usage, paper prompt alignment, and why the final report separates API audit/filtering from final DPO training.
Paper model roles | GPT-4V/GPT-4 produce fine-grained AI feedback; an open-source LVLM detector is trained from that feedback; LLaVA is used for rewriting; HSA-DPO trains the final LVLM.
Our supervision source | We use released HSA-DPO fine-grained annotations as D_FAIF instead of regenerating all GPT-4/GPT-4V annotations.
Prompt requirement | Keep appendix-aligned DDG, VCR, detector, rewrite, and severity-rubric prompts in fg_pipeline/paper/prompts.py and record prompt versions in outputs.
Current final comparison | Use the same released preference data and LLaVA-1.5-7B base for HSA-DPO versus normal DPO; report API judging as a separate audit/filter experiment.
Main failed detector lesson | Qwen2.5-VL-7B detector inference predicted 0 hallucinated rows, likely due to detector target/prompt/parser collapse or calibration rather than proof that the model family is unusable.
Detailed artifact | reports/vlm_fine_grained_feedback_methodology.md